## engineering
| RATE MY CAMPUS | [6 empty] | Period Highlight: |  |  |  |  | 43 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ENGINEERING | [6 empty] | Start Date: |  |  |  | 2016-10-17 | [10 empty] | Start Date: |  |  |  | 2016-11-14 | [8 empty] | Today's Date |  |  |  | 2016-11-28
[8 empty] | Due Date: |  |  |  | 2016-11-01 |  |  |  | (Project 3) | [6 empty] | Due Date: |  |  |  | 2016-12-08 |  |  |  | (Project 4)
|  | MEMBER | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | Oct | [14 empty] | Nov | [29 empty] | Dec
MILESTONE | TASK | ASSIGNED | START | DURATION | START | DURATION | COMPLETE | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
Project Setup | Create Github repository | SA | 5 | 1 | 5 | 1 | 100%
| Research Meteor | ALL | 1 | 3 | 1 | 3 | 100%
| Research React | ALL | 1 | 3 | 1 | 3 | 100%
| Do Meteor + React Tutorial | ALL | 4 | 2 | 4 | 2 | 100%
| Setup project base | SA | 5 | 2 | 5 | 2 | 100%
App container template | Create navbar header | SA | 5 | 1 | 5 | 1 | 100%
| Create footer | SA | 5 | 1 | 5 | 1 | 100%
| Create content container | SA | 5 | 1 | 5 | 1 | 100%
MongoDB | Create fixtures (i.e. mock data) | SA | 10 | 1 | 10 | 1 | 100%
| Create collection for buildings and its methods | SA | 10 | 1 | 10 | 1 | 100%
| Create collection for ratings and its methods | SA | 11 | 1 | 11 | 1 | 100%
| Create collection for schools and its methods |  | 13 | 1 |  |  | 0%
| Come up with schema for ratings (i.e. what to rate) | EC | 12 | 1 | 12 | 1 | 100%
| Update collection schemas | SA | 14 | 3 | 12 |  | 0%
| Add feature for user log in /sign up |  | 1 |  |  |  | 0%
Home page | Create generic button component | SA | 6 | 1 | 6 | 1 | 100%
| Create search input component | SA | 6 | 1 | 6 | 1 | 100%
| Implement search button functionality | SA | 10 | 1 | 10 | 1 | 100%
| Create recent ratings card | EC | 11 | 1 |  |  | 0%
| Implement recent ratings section |  | 12 | 2 |  |  | 0%
| Get recent ratings data from the backend | SA | 31 | 2 | 31 | 2 | 100%
| Create load more button | EC | 11 | 1 |  |  | 0%
| Implement load more button functionality |  | 11 | 1 |  |  | 0%
Search results page | Create search results page | AM | 11 | 2 | 11 |  | 25%
| Point search button action to search results page | AM | 13 | 2 | 13 |  | 0%
| Create search results list component | AM | 11 | 2 | 11 |  | 0%
| Point search result list item to details page | AM | 13 | 1 | 13 |  | 0%
Details page | Create details page | SA | 15 | 1 | 15 | 1 | 100%
| Create top section that displays information and map | SA | 15 | 1 | 15 | 1 | 100%
| Create map button and point to google maps | SA | 15 | 1 | 15 | 1 | 100%
| Get data for a building from the backend | SA | 15 | 2 | 15 | 2 | 100%
| Create add rating button |  | 1 | 1 |  |  | 0%
| Create add rating form |  | 1 | 2 |  |  | 0%
| Implement add rating functionality |  | 1 | 3 |  |  | 0%
| Create find a room button | EC | 38 | 1 | 38 | 1 | 100%
| Implement find a room functionality | EC | 38 | 2 | 38 | 2 | 100%
| Create overall quality section | SA | 15 | 2 | 15 | 2 | 100%
| Get overall quality ratings from the backend | SA | 14 | 3 | 14 | 3 | 100%
| Create reviews and ratings list component | SA | 43 | 2 | 43 |  | 50%
| Get reviews and ratings from the backend | SA | 43 | 2 | 43 | 2 | 100%
Test Suite | Research testing packages for Meteor | SA | 28 | 1 | 28 | 1 | 100%
| Research testing packages for React | SA | 28 | 1 | 28 | 1 | 100%
| Create an "API" to run tests |  | 1 | 1 |  |  | 0%
| Create a page to display API response |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%

## business
| RATE MY CAMPUS | [6 empty] | Period Highlight: |  |  |  |  | 43 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| BUSINESS | [6 empty] | Start Date: |  |  |  | 2016-10-17 | [10 empty] | Start Date: |  |  |  | 2016-11-14 | [8 empty] | Today's Date |  |  |  | 2016-11-28
[8 empty] | Due Date: |  |  |  | 2016-11-01 |  |  |  | (Project 3) | [6 empty] | Due Date: |  |  |  | 2016-12-08 |  |  |  | (Project 4)
|  | MEMBER | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | Oct | [14 empty] | Nov | [29 empty] | Dec
MILESTONE | TASK | ASSIGNED | START | DURATION | START | DURATION | COMPLETE | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
Branding | Come up with a product name | ALL | 1 | 1 | 1 | 1 | 100%
Documentation | Find Gantt Chart Tool | AM | 1 | 1 | 1 | 1 | 100%
| Setup Gantt Chart | AM | 1 | 15 | 1 | 2 | 10%
| Fill Out Gantt Chart | ALL | 1 | 10 | 4 |  | 30%
| Setup Scrum Artifacts | ALL | 1 | 10 | 4 |  | 30%
| Use-Case Diagram | EC | 9 | 3 | 14 | 1 | 100%
| State Diagram | EC | 11 | 3 | 15 | 2 | 100%
| Class Diagram | PP | 13 | 3 | 15 | 2 | 100%
| Create README | SA | 4 | 1 | 4 | 2 | 100%
Design | Create styleguide | SA | 3 | 1 | 3 | 1 | 100%
| Design home page | SA | 3 | 2 | 3 | 2 | 100%
| Design building search results page | SA | 3 | 2 | 3 | 2 | 100%
| Design room search results page | EC | 10 | 1 | 11 | 1 | 100%
| Design details page | SA | 3 | 2 | 3 | 2 | 100%
| Design rating form | EC | 10 | 1 | 11 | 1 | 100%
User Manual | Take screenshots of the website | EC | 38 | 1 |  |  | 0%
| Create instructions on how to search | EC | 41 | 1 | 41 | 1 | 100%
| Create instructions on how to read the ratings | EC | 41 | 1 | 41 | 1 | 100%
| Create instructions on how to add a rating | EC | 41 | 1 | 41 | 1 | 100%
| Create descriptions of building rating categories | EC | 40 | 1 | 41 | 1 | 100%
| Create descriptions of classroom rating categories | EC | 40 | 1 | 41 | 1 | 100%
| Add a FAQ page | EC | 40 | 1 | 41 | 1 | 100%
| Create instructions on how to contact support | EC | 38 | 1 | 40 | 1 | 100%
Deployment Plan | Research a service to host our server + costs |  | 1 |  |  |  | 0%
| Research a web domain host + costs |  | 1 |  |  |  | 0%
| Research marketing strategies + costs |  | 1 |  |  |  | 0%
Maintenance Plan | Research costs to hire developers |  | 1 |  |  |  | 0%
Research costs to hire business type peeps
| Research how to obtain updated lists of facilities |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%
|  |  | 1 |  |  |  | 0%