## project
| RATE MY CAMPUS | [6 empty] | Period Highlight: |  |  |  |  | 16 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Team ESAP | [6 empty] | Start Date: |  |  |  | 2016-10-17 | [10 empty] | Start Date: |  |  |  | 2016-11-14 | [8 empty] | Today's Date |  |  |  | 2016-10-26
[8 empty] | Due Date: |  |  |  | 2016-11-01 |  |  |  | (Project 3) | [6 empty] | Due Date: |  |  |  | 2016-12-09 |  |  |  | (Project 4)
|  | MEMBER | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | Oct | [14 empty] | Nov
MILESTONE | TASK | ASSIGNED | START | DURATION | START | DURATION | COMPLETE | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
Branding | Come up with a product name | ALL | 1 | 1 | 1 | 1 | 100%
Documentation | Find Gantt Chart Tool | AM | 1 | 1 | 1 | 1 | 100%
| Setup Gantt Chart | AM | 1 | 15 | 1 | 2 | 10%
| Fill Out Gantt Chart | ALL | 1 | 10 | 4 |  | 25%
| Setup Scrum Artifacts | ALL | 1 | 10 | 4 |  | 15%
| Use-Case Diagram |  | 9 | 3 | 10 |  | 0%
| State Diagram |  | 11 | 3 | 10 |  | 0%
| Class Diagram |  | 13 | 3 | 10 |  | 0%
| Create README | SA | 4 | 1 | 4 | 2 | 100%
Design Site | Create styleguide | SA | 3 | 1 | 3 | 1 | 100%
| Design home page | SA | 3 | 2 | 3 | 2 | 100%
| Design building search results page | SA | 3 | 2 | 3 | 2 | 100%
| Design room search results page | EC | 10 | 1 |  |  | 0%
| Design details page | SA | 3 | 2 | 3 | 2 | 100%
| Design rating form | EC | 10 | 1 |  |  | 0%
Setup project | Create Github repository | SA | 5 | 1 | 5 | 1 | 100%
| Research Meteor | ALL | 1 | 4 | 1 | 5 | 100%
| Research React | ALL | 1 | 4 | 1 | 5 | 100%
| Do Meteor + React Tutorial | ALL | 2 | 4 | 3 | 4 | 50%
| Setup project base | SA | 4 | 2 | 4 | 2 | 100%
Create App Container | Create navbar header | SA | 3 | 2 | 3 | 2 | 100%
| Create footer | SA | 3 | 2 | 3 | 2 | 100%
| Create content container | SA | 3 | 2 | 3 | 2 | 100%
MongoDB Work | Create fixtures (i.e. mock data) | SA | 9 | 1 | 10 | 1 | 100%
| Create collection for buildings | SA | 9 | 1 | 9 | 1 | 100%
| Create collection for ratings |  | 11 | 1 |  |  | 0%
| Implement buildings methods | SA | 9 | 2 | 10 | 3 | 25%
| Implement ratings methods |  | 11 | 2 |  |  | 0%
Create Home Page | Create search input component | SA | 3 | 2 | 3 | 2 | 100%
| Create generic button component | SA | 3 | 1 | 3 | 1 | 100%
| Implement search button functionality | SA | 8 | 3 | 10 | 1 | 100%
| Create recent ratings card | EC | 11 | 3 |  |  | 0%
| Create load more button | EC | 11 | 2 |  |  | 0%
| Populate recent ratings section |  | 8 | 4 |  |  | 0%
Create Building Search Results Page | Create results list component |  | 8 | 3 |  |  | 0%
| Create results display component |  | 8 | 3 |  |  | 0%
Create Building Details Page | Create add rating button |  | 8 | 1 |  |  | 0%
| Create find a room button |  | 8 | 1 |  |  | 0%
| Create top section with map button |  | 8 | 3 |  |  | 0%
| Create overall quality section component |  | 10 | 3 |  |  | 0%
| Create reviews and ratings list component |  | 12 | 4 |  |  | 0%
| Create add rating form |  | 10 | 4
Create Room Search Results Page |  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
Create Room Details Page |  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%
|  |  | 1 | 1 |  |  | 0%